## Sheet1
PROJECT X PROJECT PLAN
Task ID | Task Name | Sub Task ID | SubTask Name | Deliverables | Assignee | Estimated Day(s) | Start Date | End Date | Actual Day(s) Used | Status | Notes
1 | Project Initiation | 1.1 | Project Kickoff Meeting | Team Members List | John Kenneth Gade | 2 | 2025-03-20 | 2025-03-21 | 2 | Done
|  | 1.2 | Identifying Project Scope & Objectives | Requirements Review | Ivan Vasay | 8 | 2025-03-22 | 2025-03-29 | 8 | Done
2 | Requirement Analysis | 2.1 | Gather Functional Requirement | Project X - Client Stated Requirement | Cyril Balanay | 6 | 2025-03-30 | 2025-04-06 | 8 | Done
|  | 2.2 | Initiate an Elicitation Session with Client | Project X - Requirements Elicitation - v.1.0 | Keynt Harly Adol | 4 | 2025-04-07 | 2025-04-11 | 5 | Done
|  | 2.3 | Validate Requirements with Client | Project X - Requirements Elicitation - v.1.1 | John Kenneth Gade | 3 | 2025-04-12 | 2025-04-14 | 3 | Done
|  | 2.4 | Finalizing System Requirements | Project X - Requirements Elicitation - v.1.2 | Keynt Harly Adol | 3 | 2025-04-15 | 2025-04-17 | 3 | Done
3 | Project Design | 3 | Conceptual Design | High-Level Use Case Diagrams, Conceptual Model Traceability Matrix Project Plan | John Kenneth Gade, Keynt Harly Adol, Ivan Vasay | 10 | 2025-04-18 | 2025-04-29 | 12 | Done
4 | Documentation | 4 | Set up Version Control (Git) | Git Repository Setup Provide Access to Repository | Ivan Vasay | 1 | 2025-04-30 | 2025-04-30 | 1 | Done
5 | System Design | 5.1 | Mobile App Architecture | Framework Frontend Backend Database | Cyril Balanay | 2 | 2025-05-01 | 2025-05-02 |  | Done
|  | 5.2 | UI/UX Design | Prototype/Wireframe | John Kenneth Gade | 7 | 2025-05-03 | 2025-05-09 |  | Done
6 | Development and Implementation | 6.1 | Backend Development | Cloud Database Integration API for User Authentication QR Code Validation | Keynt Harly Adol |  | 2025-05-10 | 2025-05-09 |  | Done
|  | 6.2 | Frontend Development | User Interfaces QR Code Scanning GPS Validation | Cyril Balanay |  | 2025-05-10 | 2025-05-09 |  | Done
|  | 6.3 | Features | Generate Reports Data Exportation Location Tracking | John Kenneth Gade |  | 2025-05-10 | 2025-05-09 |  | Done
7 | Testing & Debugging | 7.1 | Unit Testing | Verified Functionality of Individual Components | Ivan Vasay |  | 2025-05-10 | 2025-05-09 |  | Done
|  | 7.2 | System Testing | Full System Integration Test |  |  | 2025-05-10 | 2025-05-09 |  | Done
|  | 7.3 | User Acceptance Testing (UAT) | Client Validation & Feedback | John Kenneth Gade |  | 2025-05-10 | 2025-05-09 |  | Done
8 | Deployment & Final Demonstration | 8.1 | Final System Review | System Deployment Final Documentation User Manual | Team Members |  | 2025-05-10 | 2025-05-09 |  | Ongoing
|  | 8.2 | Final Presentation | Project Presentation, App Demonstration |  |  | 2025-05-10 | 2025-05-09 |  | Ongoing
Formulas:
End Date = IF([Actual Day(s) Used]<>"", [Start Date] + [Actual Day(s) Used] -1, [Start Date] + [Estimated Day(s)] - 1)
Start Date = [End Date, row above] + 1